## Rotary Club
New Club Checklist
Download and adapt this checklist as required to use as a project plan to start your new Rotary club.
| Task | Action Owner | Status | Comments
Before Chartering
 | Contact the district governor for your region to discuss your interests and plans. (Tip: Your local Club and District Support representative can help, https://my.rotary.org/en/contact/representatives.)
 | Ask the district governor to assign a new club adviser and sponsor club. (Tip: While a sponsor club is not mandatory, this can increase your chances of success.)
 | Contact your local Club and District Support representative to discuss ideas for the club operating format and get preliminary approval for possible club names (https://my.rotary.org/en/contact/representatives).
 | Visit the Brand Center to become familiar with the Rotary Marks and explore available resources (https://brandcenter.rotary.org/).
 | Make a communication plan. Consider your target market and communication channels for bringing your message to a wide audience.
 | Hold a series of informational meetings to identify potential members.
 | Recruit at least 20 charter members (Tip: Clubs that charter with 25 or more members tend to have more long-term success.)
 | Hold an organizational meeting to finalize club details, such as electing club officers and agreeing on meeting format and location.
 | Set club dues amount. (Tip: Club dues will include Rotary International dues, district dues, magazine subscriptions, insurance, if required, plus any specific club component.)
 | Adopt the Standard Rotary Club Constitution, and create and adopt club bylaws at a meeting of all club members. Contact your local Club and District Support representative for regional variations (https://my.rotary.org/en/contact/representatives).
 | Fill out new club application and charter member list. All information is required.
 | Submit new club application and charter member list to the district governor for approval and signature.
 | Email new club application and charter member list to your Club and District Support representative (https://my.rotary.org/en/contact/representatives).
 | Submit US$15 per member charter fee, adding applicable local taxes if any. (Tip: Contact your local financial representative for local currency conversions and payment details, https://my.rotary.org/en/contact/representatives.)
After Chartering
 | Plan club charter celebration. (Tip: Wait until your new club has been approved by Rotary International before setting the date.)
 | Create your new club logo with approved club name and use it to order club banners, club shirt, etc.
 | Celebrate the charter and publicize the club.

## Status (hidden)
Status:
Not Started
In Progress
Complete